## Team
Team Name | Fantastic Five
Game name | (TBD)
Engine | Unity
Member | Role
Daniel Shin | Artist/Sound
Allen Zhang | Project Manager/Narrative
Andres Ruiz | Programmer
Leo Lopez | Programmer
Alejandro Marin | Programmer

## Vision_Canvas
High Level Vision Canvas
Fantastic Five
Inspirations | Genre | Core Pillars | Core Gameplay Systems | Player Experience
| 2.5D Side scroller | Stealth | Difficulties | Player feels the Thrill of avoiding obstacles and guards
| Stealth | Player use movement strategically to avoid alarms/enemies or trigger them to affect change within environment | Easy - 1 life (checkpoints) | Player feels a sense of Achievement when successfully overcoming obstacles
| Strategy | Player can use environment to hide from both active enemies and passive entities | Hard - 1 life (no checkpoints) | Player feels the Suspense of anticipating challenges ahead
| Role Play | Tools |  | Player feels the Pressure of navigating dangerous situations
|  | Player can use tools for hiding/escaping and distracting gaurds |  | Player is Challenged by puzzles unique to each level
Inside/Limbo - Dark Gloomy - Sneaking around |  | Player will gain buffs through tools acquired and utilized | Game Progression | Player feels Satisfied in collecting customizations and tools
Deus Ex - Dark, gloomy environment |  | Player can interact with the world by using technology in the environment to affect changes that help them progress through levels | Checkpoints between levels | Player experiences Excitement by successfully using stealth skills and magic tools to avoid detections
Assassin's Creed - Parkour movement - Character appearance - Stealth | IP/World | Player can strategically select tool for a given level or situation Tools are applied immediately upon picking up the tool | Progress through game by completing levels a level
Uncharted - Gameplay | Dark fantasy world | Exploration
Metal Gear Solid - Use of environment for hiding | Dark/low light aesthetic theme | Player can solve each level in a variety of ways suited to their individual play style | Stealth
Fallout - Interacting with tools to influence environment | Cutaway view of building focused on player's location within building | Player has to feel like a thief using stealth to circumvent obstacles in each la evel | AI and line of sight for the guards | Player Types
Dark Souls - Level design - Narrative - Dark, glommy world setting |  | Player can find different tools to help them achieve the goals | Alarm/Trap system for pressured situations | Strategist: Problem solvers seeking the thrill of circumventing enemies and obstacles
|  | Player can track the character as they move through the level easily | Hiding in environment | Collector: Collects all items the world has to offer
| Post Launch Plans |  |  | Optimizer: Clears the game in the minimum amount of time
| Potential sequel |  | Tools | Try Hard: Clears the game without using any tools
| DLCs - new levels - new characters - new tools - new skins |  | Interaction between player tools and environment
Tool selection menu Tools applied upon pickup for a set duration
Self-defense/disengagement system
World
Overworld display to navigate levels
Level design and layout of obstacles
Navigation to track movement of character
Narrative
Dialogue system to explain gameplay and drive light narrative
Core Gameplay Features
Unique tools to enhance different strategic styles
5 levels that offer - unique obstacles for the player - different environments - different enemies 1 level that offers: - unique obstacles for the player - a single environment - a single enemy

## Change_List
The Change list should show all the elements you added or deleted in your Review of the Design Documents
Player Experience Changes
Area | Description
Added magic and tools
Environment/background of the settings to dark fantasy
Tutorials
Game loop
Feature List Changes
Feature # | Modification
28 | Omitting Disguise Acquisition
29 | Omitting Disuise Buff System
F001b | Changed difficulty to easy, level objectives themselves are relatively easy to implement with boolean checks (ex: player picks up item, then door unlocks)
F001h | Changed difficulty to low, unity has it's own camera setups/functions to follow an object (the player)
F003c | Changed difficult to low, ending the game when caught should not be difficult
F004a | Changed priority to high since they tools are now a core component of the game
F004d | Changed priority to high since they tools are now a core component of the game
Scope Change
Area | Description
Limiting levels to 1 to 5 levels
Removed addons
Removed cutscenes
Lowering scope/complexity of tools
System Change
Area | Description
Added difficulty settings
Name of the game

## Feature_List
# | Feature Name | Top Level Description | Priority | Difficulty | Time to Complete | Risk | Comments
F001 | SYSTEM
F001a | Save/Load | Ability to save between levels and load saved data | Low | Low | Low |  | Maybe add it later if decided to expand the game size
F001b | Level Objectives | Complete level by fulfilling given objective (Finding certain items) | High | High | High
F001c | Tutorial System | Pop-ups to explain how to play game/use tools/etc. | Low | Low | Low | Potential to be too disruptive | Pop up with picture/animation of how to use given control
F001d | General Audio Setup | Audio & music for every level, detail, escaping, and etc during the game that can be toggled in settings | Low | Low | Low
F001e | General Movement | Player should be able to move in game | High | High | Low
F001f | Game DLC | Extra level / characters | Low | Low | Low
F001g | Difficulty | Two difficulty settings (Easy, Hard) | Low | Low | Low
F001h | Camera | View follows player movement as they move through the level | High | Low | Med | If implemented poorly, will make gameplay difficult
F001i | Overworld Navigation | Players navigate between levels in a higher-level view wrapping the set of levels | Med | Low | Med
F002 | GUARD
F002a | Guard Detection | Guards are able to detect player within set range | High | Low | Low | Potential to make gameplay overly difficult
F002b | Guard AI | Guards are not always stationary and can react to detection of player | High | Based on complexity | Based on complexity | If inconsistent or slow to respond can be frustrating
F002c | Detection Obstacles in Level | Detection toward player's movement and steps | Med | Med | Med | Player should be able to anticipate camera behavior
F002d | Traps | Kills player uppon interaction | Med | Med | Med
F003 | STEALTH
F003a | Alarm System | When player triggers the alarm, all gaurds within the same room start to chase the player | High | High | High | Alarm triggers should make sense to player
F003c | Game Over | The character dies if he get caught by the gaurd | High | Low | High | Shouldn't be too hard
F003d | Hiding in Environment | Using objects and hidden locations to avoid guards and detection | High | High | High | Animations/design to clarify “hidden” state
F004 | Magic Tool
F004a | Tool Acquisition | Player must have a way to acquire tools as they progress thru game | High | Low | Low |  | Not missable
F004b | Tool Inventory/Selection | Tool wheel to see set of available tools and change equipped tool in/before level | Low | Med | Med | Must not disrupt gameplay when selecting in level | Organize items by "class" (e.g throwable) maybe by color Enable sorting of inverntory by class
F004c | Tool Usage and Effects | Tools can affect physical change in surroundings and trigger events such as alerting or distracting guards/cameras | High | High | High | Animations, engine restrictions. Persistence? | Some tools are necessary while some tools are not
Every variation introduces more complexity
Must account for all aspects of environment
Effects should be consistent with player expectations
F005 | ENVIRONMENT/ART
F005a | Background | Background image for the different levels | Low | High | High
F005b | Obstacle | Objects that are not part of the | Med | Med | Med
F005c | Tools/Magic | Designs of tools, effects from using tools and magics | Med | High | Med
F005d | Player | Look of the player including different outfits | High | Med | Med
F005e | Guard | Looks / Abilities of different guards | High | Med | High
F005f | Interface | Interfaces including title page, buttons, displays, etc. | Med | Low | Low
F005g | Title | Title page art | Low | Low | Low
F006 | ANIMATION
F006a | Player | Movements and actions of the player | Med | Med | Med
F006b | Guard | Movements and actions of the guards | Med | Med | High
F006c | Obstacle | Obstacles responding to outer forces | Low | High/Low | High
F007 | SOUND
F007a | Music | Background music for each levels | Low | Low | Low
F007b | Sound effect | Sound effects from different responses, situations | Low | Low | Low
N

## Art Design
Narrative
Background | The great old one has awakened. The once glorious kingdom has been cursed by the darkness. A petty thief, locked away in a long forgotten dungeon is chosen by fate to defeat the ancient demon and lift the curse fallen upon this land.
Progress | In order to defeat the great evil, one must find three unique things, hidden away in three different places. Once the chosen one has gather all three objects, he shall step on the path to the lair of the great old one.
Ending | Ending 1: The demon has been defeated, the chosen one is enthroned to become the next king. Sitting on the throne, marks od darkness infection has appeared on his face. Ending 2: The demon has been defeated, the chosen one left to seek his next destination. However, after days, maybe years, the demon's body started to move. Suddenly, a giant, malevolent eye has opened, again......
Envrionment
Overall | Dark, glommy ruined lands filled with desperation and monstrosities
Tutorial | Dungeon with prison cells
Base | Abandoned temple with mutiple entrances to different levels, this is the place where the player can rest, chat with NPCs, manager the inventory and head for thr next level
Level 1 | Haunted forest, dark and creepy, where ghosts and beasts wander | Creepy, dark-grey
Level 2 | Defiled village, disgusting place where diseases spread, rotting creatures everywhere | Disgusting, yellow
Level 3 | Castle, fallen capital of a once-mighty kingdom, the glory of its past is still faintly visible
Level 4 | Cradle of darkness, a dark cave where demons gather | Dark, black
Game Play Elements
Tools | The tool system is divided into two subsystems: magic spells and consumable tools. magic spells take some time to cool down after using. Magic tools are used to enhanced the character's own abilities while tool objects are used on the guards, such as distracting them.
Companion | A guardian spirit that can cast spells to help the player through the game
Traps
Navigation aspects | Wooden ladders, ropes, elevators
Main Character
Default | Apperance Low-poly character with a hood and dark overall color. Background A nameless thief chosen by fate to break the curse fallen upon this kingdom
Skins | Character will have skins as different colors or patterns.
Equipments | Characters will have various types of head gears the player choose from
Guard
Jailers | skeleton soldiers who guard the dungeon
Ghosts | semi-transparent entities who lurk in the forest; hard to spot; screams when alerted
Villagers | half-rotten villagers who reside in the forsaken defiled village, usually wander in groups; would call for others when alerted
Knights | heavy-armored royal guards who still patrol in the fallen castle; they move slowly but are very persistent
Demons | dark creatures who reside in their lair; move very quickly
UI

## Tech_Design
Ver | Modified
Ref # | System Name | Feature Supported | Feature Specifics | Priority | Difficulty | Risk | Time Estimation | Comments
F001 | System
F001a |  | Save/Load |  | Low | Low |  | 1 week | Maybe add it later if decided to expand the game size
Save
Load
Checkpoint
F001b |  | Level Objectives |  | High | Low |  | 1 week | Should be relativiely easy to implement, player picks up item and some part of the level is unlocked
Complete condition
|  |  | Return to base |  |  |  |  | This refers to some easy path back to the base of the map.
F001c |  | Tutorial System |  | Low | Low | Potential to be too disruptive | 1 week | Pop ups with pictures of how to use a given tool/control
Narratives
Control tutorials
Tool tutorials
F001d |  | General Audio Setup |  | Low | Low |  | 1 week
|  |  | Volume control |  |  |  |  | Changing volume of sfx/bgm/voice
F001e |  | General Movement |  | High | High | More complicated forms of movement can increase the difficulty of implementation | 3 weeks
Walk
Crouch
Run
Jump
Climb/Parkour
F001f |  | Game DLC |  | Low | Low |  | 1 week
Store
Transaction
Acquisition
F001g |  | Difficulty |  | Low | Low |  | 1 week
Difficulty selection
Easy
Hard
F001h |  | Camera |  | High | Low | If implemented poorly, it can make the game more difficult or awkaward | 1 week
Transition
Tracking player
F001i |  | Overworld Navigation |  | Med | Low |  | 1 week
Level entry
F002 | Guard
F002a |  | Guard Detection |  | High | Low | Has the potential to make the game overly difficult | 1 week
Line of sight
Sound dedection
Visual indicator
F002b |  | Guard AI |  | High | High | A poor implementation can make the game easy or frustrating | 3 weeks | Guard's interaction with the player should be well thought out
|  |  | Follow player |  |  |  |  | Include search and pursit
Static guard
Follow a path
Attack
F002c |  | Detection Obstacles in Level |  | Med | Med |  | 2 weeks
Alert
F002d |  | Traps |  | Med | Med | Need to find a good balance of number and difficulty of traps as to not frustrate the player | 2 weeks
|  |  | Collision |  |  |  |  | Death upon collision
Activation
Movements
F003 | Stealth
F003a |  | Alarm System |  | High | High | Alarm triggers should make sense to the palyer | 3 weeks
Alarm sound
Visual indicatior
F003c |  | Game Over |  | High | Low |  | 1 week
Game over condition
Return last checkpoint
F003d |  | Hiding in Environment |  | High | High | Animations/design to clarify “hidden” state | 3 weeks
Enter hiding
Bypass guard detection
F004 | Magic Tool
F004a |  | Tool Acquisition |  | High | Low |  | 1 week
Tool placement
Tool acquisition
F004c |  | Tool Inventory/Selection |  | Low | Med | Must not disrupt gameplay when selecting in level | 1 week
Inventory system
Inventory UI
Tool equipment
F004d |  | Tool Usage and Effects |  | High | High | Animations can be diffult to make/find. Each tool that gets implemented has the potential to drastically change the flow of a level. | 3 weeks | Some tools may be necessary to a level/area while others are not
Tool usage
Tool effects
F005 | Environment
F005a |  | Background |  | Low | High |  | 2 weeks | Should be carefully chosen and well thought out to fit the art design
Background transition
Background tracking
F005b |  | Obstacle |  | Med | Med |  | 2 weeks
Obstacle hitbox
Obstacle effect
F005c |  | Tools/Magic |  | Med | High |  | 3 weeks
Tool special effect
F005d |  | Player |  | High | Med |  | 2 weeks
Player equipment
F005e |  | Guard |  | High | Med |  | 2 weeks
F005f |  | Interface |  | Med | Low |  | 1 week
Button
Information
Narration
F005g |  | Title |  | Low | Low |  | 1 week
|  |  | Options |  |  |  |  | Store, settings, continue, new game, etc.
Animation
F006a |  | Player |  | Med | Med |  | 2 weeks
Animation activation
Animation deactivation
F006b |  | Guard |  | Med | Med |  | 2 weeks
Animation activation
Animation deactivation
F006c |  | Obstacle |  | Low | High/Low | Potential to be difficult depending on the obstacle we decide to create | 1-3 weeks
Animation activation
Animation deactivation
F007 | Sound
F007a |  | Music |  | Low | Low |  | 1 week
Music activation
Music dactivation
F007b |  | Sound effect |  | Low | Low |  | 1 week
Sound effect activation

## Milestones
Project: | Project Disguised
Date | Milestone | Task | Assets to be created | Estimated time | % Complete | Comments
Week 6 | Design | Finish Design Documents | Spreadsheets |  |  | Currently working on it
Week 7 | Feature | Player Movement + Spells/Tools | Character model |  |  | Run/Sneak/Run. 3 Weeks to work on every tool (will work on them alphabetically)
Week 8 | Feature | AI Controls + Spells/Tools | Guards |  |  | Guards should be able to respond to player movement
Week 9 |  | Save/Load and Game Over | Menus/UI |  |  | Should be able to save after finishing a level, load progress, and lose if caught.
Week 10 | Feature | Detection + Spells/Tools | Detection System |  |  | Traps and detection obstacles like cameras.
Week 11 |  | Player Movement + AI |  |  |  | More time to refine movement/AI after other things have been finished
Week 12 | Feature | Alarm System
Week 13 |  | Level Design |  |  |  | The rest of the time is used to create levels once we finish everything else
Week 14 | Feature
Week 15 |  | QA
Week 16 |  | Final Touches on Environment/Art
Daniel
Week 6 | Art/Animation | Base mesh/Main Character/ Player Animation | 3D models/Animations | 3 hours | 100% | Minimum meshes to start on the system building
Week 7 | Art/Animation | Companion/Guard/Guard Animation | 3D models/Animations | 5 hours | 100%
Week 8 | Art/Animation | Interface/Obstacle/Obstacle Animation | 3D models/Animations/Images | 5 hours | 100%
Week 9 | Art | Level Design | 3D models | 3 hours
Week 10 | Art | Spells/Tools | 3D models | 5 hours
Week 11 | Sound | Sound effect | Sound files | 3 hours
Week 12 | Art | Background/Title | Images | 3 hours
Week 13 | Art/Sound | Music/Player equipment | Sound files | 3 hours
Allen
Week 6 & 7 | Narrative | Basic structure of the storyline | narrative | 5 hours | 50 | Still working on it
Week 8 & 9 | Narrative | Details & Scripts & Item descriptions | Scripts & Item descriptions | 5 hours
Week 10 | Level design | Level design for the tutorial | Tutorial | 5 hours
Week 11 & 12 | Level design | Level design for the Level 1 and 2 | Level 1 & 2 | 8 hours
Week 13 & 14 | Level design | Level design for the Level 3 | Level 3 | 6 hours
Week 15 & 17 | Level design | Level design for the Level 4 | Level 4 | 6 hours
Anmation System | fnfn

## Risk Register
Risk Register
[6 empty] | Probability | Impact
ID # | Name | Area of Risk | Quick Description | Owner | Status | (1-5) | (1-5) | Priority | Mitigation | Recovery
1 | Schedule | programming/art/narrative/sounds | project schedule is not clearly defined/updated or understood | Lead Programmer | open | 4 | 4 | HIGH | weekly updates on scheduling | make cuts since there are no time entensions
2 | Parkour | programming | parkour might add unnecesary complication to level design | programmers | open | 4 | 3 | LOW | design levels so that completion is possible without parkour | remove parkour and adjust level design so it is not necesary
3 | Unity Tools | programming/art | most of team is unfamilar with Unity | Fantastic Five | open | 3 | 5 | HIGH | Unity tutorials | coordinate with lead programmer to make necessary changes