## Team
Team Name | Fantastic Five
Game name | Dim Light
Engine | Unity
Member | Role
Daniel Shin | Artist/Sound
Allen Zhang | Project Manager/Narrative
Andres Ruiz | Programmer
Leo Lopez | Programmer
Alejandro Marin | Programmer

## Vision_Canvas
High Level Vision Canvas
Team name: Fantastic Five
Project name: Dim Light
Inspirations | Genre | Core Pillars | Core Gameplay Systems | Player Experience
| 2.5D Side scroller | Stealth | Difficulties | Player feels the Thrill of avoiding obstacles and guards
| Stealth | Player use movement strategically to avoid alarms/enemies or trigger them to affect change within environment | Easy - 1 life (checkpoints) | Player feels a sense of Achievement when successfully overcoming obstacles
| Strategy | Player can use environment to hide from both active enemies and passive entities | Hard - 1 life (no checkpoints) | Player feels the Suspense of anticipating challenges ahead
| Role Play | Tools & Magic |  | Player feels the Pressure of navigating dangerous situations
|  | Player can collect new tools and magical spells during their game progress |  | Player is Challenged by puzzles unique to each level
Inside/Limbo - Dark Gloomy - Sneaking around |  | Player can cast magical spells through the companion to help them progress through levels | Game Progression | Player feels Satisfied in collecting tools and learning new magic spells
Deus Ex - Dark, gloomy environment |  | Player can use tools for hiding/escaping and distracting gaurds in order to progress through levels | Checkpoints between levels | Player experiences Excitement by successfully using stealth skills and magic tools to avoid detections
Assassin's Creed - Parkour movement - Character appearance - Stealth | IP/World | Player can strategically select tool and magic for a given level or situation | Progress through game by completing levels the level
Uncharted - Gameplay | Dark fantasy world | Exploration
Metal Gear Solid - Use of environment for hiding | Dark/low light aesthetic theme | Player can solve each level in a variety of ways suited to their individual play style | Stealth
Fallout - Interacting with tools to influence environment | Cutaway view of building focused on player's location within building | Player will act like a thief using stealth to circumvent obstacles in each level | AI and line of sight for the guards | Player Types
Dark Souls - Level design - Narrative - Dark, glommy world setting |  | Player can find different tools and magical spells to help them achieve the goals | Alarm/Trap system for pressured situations | Strategist: Problem solvers seeking the thrill of circumventing enemies and obstacles
|  | Player can track the character as they move through the level easily | Hiding in environment | Collector: Collects all items the world has to offer
| Post Launch Plans |  |  | Optimizer: Clears the game in the minimum amount of time
| Potential sequel |  | Tools & Magic | Try Hard: Clears the game without using any tools
| DLCs - new levels - new characters - new tools - new skins |  | Interaction between player tools, companion magic and environment
Tool, magic selection menu
Self-defense/disengagement system
World
Overworld display to navigate levels
Level design and layout of obstacles
Navigation to track movement of character
Narrative
Dialogue system to explain gameplay and drive light narrative
Core Gameplay Features
Unique tools to enhance different strategic styles
5 levels that offer - unique obstacles for the player - different environments - different enemies 1 levels that offers - Obstacles for the player - A gaurd enemy - a single environment

## Change_List
Player Experience Changes
Area | Description
Added magic and tools
Environment/background of the settings to dark fantasy
Tutorials
Game loop
Feature List Changes
Feature # | Modification/Omissions
28 | Omitting Disguise Acquisition
29 | Omitting Disuise Buff System
F001a | Save/Load was implemented but not ultimately used due to scope and lack of content to save or load
F001b | Changed difficulty to easy, level objectives themselves are relatively easy to implement with boolean checks (ex: player picks up item, then door unlocks)
F001c | Omitted due to scope
F001d | Omitted due to scope
F001f | Omitted due to scope
F001g | Omitted for simplicity
F001h | Changed difficulty to low, unity has it's own camera setups/functions to follow an object (the player)
F001i | Omitted due to scope
F002b | Omitted due to scope
F002c | Omitted for simplicity
F003a | Omitted for simplicity
F003c | Changed difficult to low, ending the game when caught should not be difficult
F003d | Omitted for simplicity
F004a | Changed priority to high since the tools are now a core component of the game
F004b | Omitted due to scope
F004d | Changed priority to high since the tools are now a core component of the game
F005c | Omitted for simplicity
F006c | Omitted due to scope
Scope Change
Area | Description
Limiting levels to 1 to 5 levels
Removed load/save since there is only one basic level
Removed addons
Removed cutscenes
Lowering scope/complexity of tools
Removed dialogues and scripts and tells the backgrough narrative
Lowering scope of the types of guards
Removed magic spells and companion system
System Change
Area | Description
Added difficulty settings
Name of the game

## Feature_List
# | Feature Name | Top Level Description | Priority | Difficulty | Time to Complete | Risk | Comments
F001 | SYSTEM
F001a | Save/Load | Ability to save between levels and load saved data | Low | Low | Low |  | Maybe add it later if decided to expand the game size
F001b | Level Objectives | Complete level by fulfilling given objective (Finding certain items) | High | High | High
F001c | Tutorial System | Pop-ups to explain how to play game/use tools/etc. | Low | Low | Low | Potential to be too disruptive | Pop up with picture/animation of how to use given control
F001d | General Audio Setup | Audio & music for every level, detail, escaping, and etc during the game that can be toggled in settings | Low | Low | Low
F001e | General Movement | Player should be able to move in game | High | High | Low
F001f | Game DLC | Extra level / characters | Low | Low | Low
F001g | Difficulty | Two difficulty settings (Easy, Hard) | Low | Low | Low
F001h | Camera | View follows player movement as they move through the level | High | Low | Med | If implemented poorly, will make gameplay difficult
F001i | Overworld Navigation | Players navigate between levels in a higher-level view wrapping the set of levels | Med | Low | Med
F002 | GUARD
F002a | Guard Detection | Guards are able to detect player within set range | High | Low | Low | Potential to make gameplay overly difficult
F002b | Guard AI | Guards are not always stationary and can react to detection of player | High | Based on complexity | Based on complexity | If inconsistent or slow to respond can be frustrating
F002c | Detection Obstacles in Level | Detection toward player's movement and steps | Med | Med | Med | Player should be able to anticipate camera behavior
F002d | Traps | Kills player uppon interaction | Med | Med | Med
F003 | STEALTH
F003a | Alarm System | When player triggers the alarm, all gaurds within the same room start to chase the player | High | High | High | Alarm triggers should make sense to player
F003c | Game Over | The character dies if he get caught by the gaurd | High | Low | High | Shouldn't be too hard
F003d | Hiding in Environment | Using objects and hidden locations to avoid guards and detection | High | High | High | Animations/design to clarify “hidden” state
F004 | Magic Tool
F004a | Tool Acquisition | Player must have a way to acquire tools as they progress thru game | High | Low | Low |  | Not missable
F004b | Tool Inventory/Selection | Tool wheel to see set of available tools and change equipped tool in/before level | Low | Med | Med | Must not disrupt gameplay when selecting in level | Organize items by "class" (e.g throwable) maybe by color Enable sorting of inverntory by class
F004c | Tool Usage and Effects | Tools can affect physical change in surroundings and trigger events such as alerting or distracting guards/cameras Tools give players buffs to aid in aid in clearing the level surpassing the guards | High | High | High | Animations, engine restrictions. Persistence? | Some tools are necessary while some tools are not
Every variation introduces more complexity
Must account for all aspects of environment
Effects should be consistent with player expectations
F004d | Companion | Companion follows the player around casting magic that helps the player | High | High | High
F005 | ENVIRONMENT/ART
F005a | Background | Background image for the different levels | Low | High | High
F005b | Obstacle | Objects that are not part of the | Med | Med | Med
F005c | Tools/Magic | Designs of tools, effects from using tools and magics | Med | High | Med
F005d | Player | Look of the player including different outfits | High | Med | Med
F005e | Guard | Looks / Abilities of different guards | High | Med | High
F005f | Interface | Interfaces including title page, buttons, displays, etc. | Med | Low | Low
F005g | Title | Title page art | Low | Low | Low
F006 | ANIMATION
F006a | Player | Movements and actions of the player | Med | Med | Med
F006b | Guard | Movements and actions of the guards | Med | Med | High
F006c | Obstacle | Obstacles responding to outer forces | Low | High/Low | High
F007 | SOUND
F007a | Music | Background music for each levels | Low | Low | Low
F007b | Sound effect | Sound effects from different responses, situations | Low | Low | Low
N

## Feature Specs
# | Feature Name | Details
F001 | SYSTEM
F001a | Save/Load
F001b | Level Objectives | A key will be placed on a specific place in the level. If the player collides with the key, the key disappears and the door to the exit opens. Without the key collected, the door will stay shut. Upon reaching the exit, the player wins.
F001c | Tutorial System
F001d | General Audio Setup
F001e | General Movement | Player will be able to crouch, crouch walk, run, jump (W or Space), crouch jump (powered jump), move left (A or <-), and move right (D or ->).
F001f | Game DLC
F001g | Difficulty
F001h | Camera | The camera is fixed and centered at the player and it moves along with the player's movements, alterations to the X, Y, and Z coordinates will tilt the camera around the player (the camera keeps the player centered). Changes to the Z will move the camera closer/further away
F001i | Overworld Navigation
F002 | GUARD
F002a | Guard Detection | When the player is within the enemy's field of view and are visible, the player will be caught rendering a game over. Handled similarly to traps(F002d
F002b | Guard AI
F002c | Detection Obstacles in Level
F002d | Traps | Collision with traps is handled similarly to Tool Acquisition(F004a). Instead of colliding with a object with a specific tag, however, we wait to see the player collide with an object pertaining to a specific layer. The traps have a layer called "Traps". Any object with this label will kill the player upon collision.
F003 | STEALTH
F003a | Alarm System
F003c | Game Over | The player loses when caught by a guard or killed by a trap. The level state resets and the player is sent back to the beginning of the level.
F003d | Hiding in Environment
F004 | Magic Tool
F004a | Tool Acquisition | Tool acquisition is handled through collision detection with an item of a specific tag. Ex: for invisibility, the tag is "InvisiblePickup".
F004b | Tool Inventory/Selection
F004c | Tool Usage and Effects | Upon colliding with an object of the tag "InvisiblePickup", the player's opacity will be set to about half it's current value and the guard's patrol script will no longer try to detect the player (thus ignoring the death condition). In addition, a timer of about 10 seconds will be started. This is done by saving the current time and waiting for it to reach a value 10 seconds after that saved time.
F004d | Companion
F005 | ENVIRONMENT/ART
F005a | Background | Dark, gloomy dungeon with skeleton gaurds moving around
F005b | Obstacle | Player must use their movement options to get past obstacles (boxes, tables, etc) as well as finding keys to unlock doors.
F005c | Tools/Magic | Tools are 3D potions with different colored liquids that are placed on the level. These potions sit on the ground and activates the ability when the player collides with the model. Model will be created with Blender. Will be made of one mesh.
F005d | Player | Black 3D low poly character with a hoodie on with basic bones (arms, legs, head, torso). Model will be created with Blender. Will have two major meshes: body and the hood)
F005e | Guard | Yellow 3D low poly skeleton model with basic bones (arms, legs, head, torso). Will be holding a low poly sword. Model will be created with Blender. Will have two major meshes: body and the hood)
F005f | Interface | Basic menus with buttons to transition between scenes or quit the application.
F005g | Title Screen | Buttons include new game, continue, store, and quit. New game and continue start game since save/load was cut. Store is not implemented since DLC was cut and quit closes application. The background image is a fantasy path leading to a castle.
F005h | Game Over Screen | Buttons include retry and quit. Quit closes application but retry is bugged due to some integration issues. The background image is a fantasy dungeon in a castle.
F006 | ANIMATION
F006a | Player | Animations of Player doing following activities: stand, crouch, crouch walk, run, jump. Will be using free animations found in Maximo.com
F006b | Guard | Animations of the skeleton standing and walking. Will be using free animations found in Maximo.com
F006c | Obstacle
F007 | SOUND
F007a | Music | Music includes in-game background music and the title music
F007b | Sound effect | Sound effects correspond to the player and AI's actions, such as walking and opening doors

## Art Design
Narrative
Background | The great old one has awakened. The once glorious kingdom has been cursed by the darkness. A petty thief, locked away in a long forgotten dungeon is chosen by fate to defeat the ancient demon and lift the curse fallen upon this land.
Progress | In order to defeat the great evil, one must find three unique things, hidden away in three different places. Once the chosen one has gather all three objects, he shall step on the path to the lair of the great old one.
Ending | Ending 1: The demon has been defeated, the chosen one is enthroned to become the next king. Sitting on the throne, marks od darkness infection has appeared on his face. Ending 2: The demon has been defeated, the chosen one left to seek his next destination. However, after days, maybe years, the demon's body started to move. Suddenly, a giant, malevolent eye has opened, again......
Envrionment
Main concept | Dark, glommy ruined lands filled with desperation and monstrosities
(Image from the game)
Tutorial | Dungeon with prison cells
Base | Abandoned temple with mutiple entrances to different levels, this is the place where the player can rest, chat with NPCs, manager the inventory and head for thr next level
Level 1 | Haunted forest, dark and creepy, where ghosts and beasts wander | Creepy, dark-grey
Level 2 | Defiled village, disgusting place where diseases spread, rotting creatures everywhere | Disgusting, yellow
Level 3 | Castle, fallen capital of a once-mighty kingdom, the glory of its past is still faintly visible
Level 4 | Cradle of darkness, a dark cave where demons gather | Dark, black
Game Play Elements
Tools | The tool system is divided into two subsystems: magic spells and consumable tools. magic spells take some time to cool down after using. Magic tools are used to enhanced the character's own abilities while tool objects are used on the guards, such as distracting them.
Companion | A guardian spirit that can cast spells to help the player through the game
Traps
Navigation aspects | Wooden ladders, ropes, elevators
Main Character
Default | Apperance Low-poly character with a hood and dark overall color. Background A nameless thief chosen by fate to break the curse fallen upon this kingdom
Skins | Character will have skins as different colors or patterns.
Equipments | Characters will have various types of head gears the player choose from
Guard
Jailers | skeleton soldiers who guard the dungeon
Ghosts | semi-transparent entities who lurk in the forest; hard to spot; screams when alerted
Villagers | half-rotten villagers who reside in the forsaken defiled village, usually wander in groups; would call for others when alerted
Knights | heavy-armored royal guards who still patrol in the fallen castle; they move slowly but are very persistent
Demons | dark creatures who reside in their lair; move very quickly
UI

## Tech_Design
Ver | Modified
Ref # | System Name | Feature Supported | Feature Specifics | Priority | Difficulty | Risk | Time Estimation | Comments
F001 | System
F001a |  | Save/Load |  | Low | Low |  | 1 week | Maybe add it later if decided to expand the game size
Save
Load
Checkpoint
F001b |  | Level Objectives |  | High | Low |  | 1 week | Should be relativiely easy to implement, player picks up item and some part of the level is unlocked
Complete condition
|  |  | Return to base |  |  |  |  | This refers to some easy path back to the base of the map.
F001c |  | Tutorial System |  | Low | Low | Potential to be too disruptive | 1 week | Pop ups with pictures of how to use a given tool/control
Narratives
Control tutorials
Tool tutorials
F001d |  | General Audio Setup |  | Low | Low |  | 1 week
|  |  | Volume control |  |  |  |  | Changing volume of sfx/bgm/voice
F001e |  | General Movement |  | High | High | More complicated forms of movement can increase the difficulty of implementation | 3 weeks
Walk
Crouch
Run
Jump
Climb/Parkour
F001f |  | Game DLC |  | Low | Low |  | 1 week
Store
Transaction
Acquisition
F001g |  | Difficulty |  | Low | Low |  | 1 week
Difficulty selection
Easy
Hard
F001h |  | Camera |  | High | Low | If implemented poorly, it can make the game more difficult or awkaward | 1 week
Transition
Tracking player
F001i |  | Overworld Navigation |  | Med | Low |  | 1 week
Level entry
F002 | Guard
F002a |  | Guard Detection |  | High | Low | Has the potential to make the game overly difficult | 1 week
Line of sight
Sound dedection
Visual indicator
F002b |  | Guard AI |  | High | High | A poor implementation can make the game easy or frustrating | 3 weeks | Guard's interaction with the player should be well thought out
|  |  | Follow player |  |  |  |  | Include search and pursit
Static guard
Follow a path
Attack
F002c |  | Detection Obstacles in Level |  | Med | Med |  | 2 weeks
Alert
F002d |  | Traps |  | Med | Med | Need to find a good balance of number and difficulty of traps as to not frustrate the player | 2 weeks
|  |  | Collision |  |  |  |  | Death upon collision
Activation
Movements
F003 | Stealth
F003a |  | Alarm System |  | High | High | Alarm triggers should make sense to the palyer | 3 weeks
Alarm sound
Visual indicatior
F003c |  | Game Over |  | High | Low |  | 1 week
Game over condition
Return last checkpoint
F003d |  | Hiding in Environment |  | High | High | Animations/design to clarify “hidden” state | 3 weeks
Enter hiding
Bypass guard detection
F004 | Magic Tool
F004a |  | Tool Acquisition |  | High | Low |  | 1 week
Tool placement
Tool acquisition
F004c |  | Tool Inventory/Selection |  | Low | Med | Must not disrupt gameplay when selecting in level | 1 week
Inventory system
Inventory UI
Tool equipment
F004d |  | Tool Usage and Effects |  | High | High | Animations can be diffult to make/find. Each tool that gets implemented has the potential to drastically change the flow of a level. | 3 weeks | Some tools may be necessary to a level/area while others are not
Tool usage
Tool effects
F005 | Environment
F005a |  | Background |  | Low | High |  | 2 weeks | Should be carefully chosen and well thought out to fit the art design
Background transition
Background tracking
F005b |  | Obstacle |  | Med | Med |  | 2 weeks
Obstacle hitbox
Obstacle effect
F005c |  | Tools/Magic |  | Med | High |  | 3 weeks
Tool special effect
F005d |  | Player |  | High | Med |  | 2 weeks
Player equipment
F005e |  | Guard |  | High | Med |  | 2 weeks
F005f |  | Interface |  | Med | Low |  | 1 week
Button
Information
Narration
F005g |  | Title |  | Low | Low |  | 1 week
|  |  | Options |  |  |  |  | Store, settings, continue, new game, etc.
F006 | Animation
F006a |  | Player |  | Med | Med |  | 2 weeks
Animation activation
Animation deactivation
F006b |  | Guard |  | Med | Med |  | 2 weeks
Animation activation
Animation deactivation
F006c |  | Obstacle |  | Low | High/Low | Potential to be difficult depending on the obstacle we decide to create | 1-3 weeks
Animation activation
Animation deactivation
F007 | Sound
F007a |  | Music |  | Low | Low |  | 1 week
Music activation
Music dactivation
F007b |  | Sound effect |  | Low | Low |  | 1 week
Sound effect activation

## Milestones
Project: | Project Dim Light
Weeks | Milestone | Task(s) | % Complete | Dependencies | Owners | Comments
Weeks 6 - 8 | Animations (F006a) (1 / 3) | Player Animations: WITH BASIC MODEL - Idle [COMPLETE] - Walking [COMPLETE] - Running [COMPLETE] - Crouching [COMPLETE] - Jumping [COMPLETE] - Climbing [COMPLETE] - Parkour [COMPLETE] | 100% | None | LEAD: Daniel
| Player (F001E) | Basic Movement: - Idle [COMPLETE] - Walking [COMPLETE] - Running [COMPLETE] - Jumping - Crouching - Climbing - Parkour | ~50% | None | LEAD: Leo Help: Allen | - Might need to cutoff a few kinds of movements - parkour may be too complex for me - climbing might be too complex for me - little work time available (other classes have been demanding)
| Guard (F002a) (1 / 3) | Detection System: - Create object to represent guard [COMPLETE] - Create object to represent player [COMPLETE] - Create line of sight - Create visual indicator | ~50% | None | LEAD: Alex Help: Allen | - monitor issues - demanding classes - tutorials in complete 3D motion
| UI (F005f) | Menu: - Create basic main screen - Create basic exit screen - Continue - Load [COMPLETE] - Save [COMPLETE] | ~33% | None | LEAD: Andres | - demanding classes - band
| Art / Narrative (F006a) | Art: - select art for future player model [COMPLETE] - select background for level [COMPLETE] - select art for floor [COMPLETE] - select art for tools - select art for companion [COMPLETE] Narrative: - develop basic plot points [COMPLETE] - develop narrative option for tutorial - develop narrative options for guards - develop narrative options for player - develop descriptions for tools | ~ 50% | None | LEADS: Daniel, Allen Help: Andres
Weeks 9 - 10 | INTEGRATION ATTEMPT (1 / 2) | Push to GitHub: - Get animations into a folder [COMPLETE] - Get guard sample into game - Get player sample into game [COMPLETE] - Get Menu into game - Apply art background - Insert floor design [COMPLETE] | ~25% | None (just try to integrate what we have) | ENTIRE TEAM | - Incomplete parts in first three weeks :( Github problems - might be easier to keep tasks going on their own seperate tracks and retry integration later - demanding schedules - extended to another week (10)
| Animations (F006) (2 / 3) | Player Animations: ACTUAL MODEL FOR GAME - Idle [COMPLETE] - Walking [COMPLETE] - Running [COMPLETE] - Crouching [COMPLETE] - Jumping [COMPLETE] - Climbing [COMPLETE] - Parkour [COMPLETE] | 100 % |  | LEAD: Daniel
WEEKS 11 - 13 | Animations (F006) (3 / 3) | Guard Animations: ACTUAL MODEL FOR GAME - Idle [COMPLETE] - Walking [COMPLETE] Companion Animations: - Choose model [COMPLETE] - Float [COMPLETE] | 100 % |  | LEAD: Daniel
| Player (F001e, F006c) (2 / 3) | Basic Movement: - Jumping [COMPLETE] - Double Jump? [COMPLETE] - Crouching - Turning Animation System: - Idle [COMPLETE] - Walking - Jumping - Crouching | ~33% | Player (1 / 3) Animations (2 / 3) | LEAD: Leo Help: Allen | - Extremely confusing, tutorials aren't helping - demanding classes
| Guard (F002a, F002b) (2 / 3) | Detection System: - Create line of sight [COMPLETE] - Create visual indicator [COMPLETE] - Actually detect object in line of sight [COMPLETE] - Apply guard in a 2D environment - AI? - Patrolling (walking path) guard - Still/Stationary guard [COMPLETE] - Chasing guard Alarm System: - Alarm sound - Guards aware of alarm | ~66% | None | LEAD: Alex Help: Allen | - demanding classes - guards proving to be more difficult than anticipated - might need to cutoff certain kinds of guards - alarm system is hard :(
| Art / UI (F005f) | Menu: - Create basic main screen [COMPLETE] - Create basic exit screen [COMPLETE] Art: - select art for tools [COMPLETE] - select art for menu screens [COMPLETE] | 100% | None | LEAD: Andres | - demanding classes - band
| Narrative | Narrative: - develop narrative option for tutorial [COMPLETE] - develop narrative options for guards [COMPLETE] - develop narrative options for player [COMPLETE] - develop descriptions for tools | ~ 90% | None | LEADS: Allen | *******UPDATE FROM WEEK 14-15 ******* Allens computer broke, losing all the narrative we had, so cutting it off RIP Allens Computer :(
| Camera Movement (F001h) | Focus: - Follow player | 100% | None | LEAD: Leo
WEEKS 14 - 15 | Player (F006c, F001e) (3/3) | Basic Movement: - Crouching [COMPLETE] (thanks Alex) - Powered Crouch Jump [COMPLETE] (thanks Alex) - Turning [COMPLETE] Animation System: - Idle [COMPLETE] - Walking [COMPLETE] - Jumping [COMPLETE] - Crouching [COMPLETE] (thanks Alex) | 100% | Player (2 / 3) | LEADS: Leo, Alex | - finite state machines - No time for companions (cutoff due to scope)
| Guard (F002b) (3 / 3) | Detection System: - Apply guard in a 2D environment [COMPLETE] - Patrolling (walking path) guard [COMPLETE] - Succesfully detect and kill player [COMPLETE] | 100% | Guard (2 / 3) Player (General) | LEAD: Alex
| Level Design (F005) | 1st (and only) level: - Obstacles(Crates, tables, walls) [COMPLETE] - Floor w/ art [COMPLETE] - Basic design [COMPLETE] - Target door (to beat the level) placement [COMPLETE] - Player placement [COMPLETE] - Tool placement [COMPLETE] - Guard placement [COMPLETE] | 100% | Traps Tool Player (3 / 3) Guard (3 / 3) | LEAD: Daniel Help: Alex
| Sounds (F007, F001d) | Level: - Background music [COMPLETE] Pickups: - Door Unlock [COMPLETE] Player: - Death [COMPLETE] - Win! [COMPLETE] | 100% | Guard Player (3 / 3) Game State | LEAD: Alex Help: Allen, Daniel
| Traps (F002d) | - Falling Crate [COMPLETE] - Floor Trap [COMPLETE] - Death upon collision [COMPLETE] | 100% | Player (3 / 3) | LEAD: Alex
| Tools (F004, F005c) | Invis Tool: - Apply timer [COMPLETE] - Make player opaque [COMPLETE] - Detect collision [COMPLETE] Speed Tool: - Apply Timer [COMPLETE] - Increase Player Speed [COMPLETE] - Detect Collision [COMPLETE] | 100% | Player (3 / 3) | LEAD: Leo Help:Alex
| Game State (F001b, F003c) | Completion: - Key to unlock door [COMPLETE] - Door locked without key [COMPLETE] - Reach the end (Door)[COMPLETE] - Menu to play again upon succesful completion of level [COMPLETE] Losing State: - Death when in guard's vision [COMPLETE] | 100% | Level Design Player (3 / 3) Guard (3 / 3) Tools | LEAD: Alex
| INTEGRATION ATTEMPT (2 / 2) | Manually Integrate: - Push necessay files to Google Drive [COMPLETE] - Integrate into one project [COMPLETE] - Make a build [COMPLETE] | 100% | Everything | ENTIRE TEAM
| UPDATE DOCUMENTATION :^) | - Update all the cuts :) | 10% | Everything | ENTIRE TEAM
WEEK 16 | UPDATE DOCUMENTATION :^) | - Update all the cuts :) | ~100%? | Everything | ENTIRE TEAM

## Risk Register
Risk Register
[6 empty] | Probability | Impact
ID # | Name | Area of Risk | Quick Description | Owner | Status | (1-5) | (1-5) | Priority | Mitigation | Recovery
1 | Schedule | programming/art/narrative/sounds | project schedule is not clearly defined/updated or understood | Lead Programmer | open | 4 | 4 | HIGH | weekly updates on scheduling | make cuts since there are no time entensions
2 | Parkour | programming | parkour might add unnecesary complication to level design | programmers | open | 4 | 3 | LOW | design levels so that completion is possible without parkour | remove parkour and adjust level design so it is not necesary
3 | Unity Tools | programming/art | most of team is unfamilar with Unity | Fantastic Five | open | 3 | 5 | HIGH | Unity tutorials | coordinate with lead programmer to make necessary changes

## QA Test Plan
QA Test Plan |  | Project: Dim Light
Date | Build # | Tester Name
2019-12-06
Test # | Unit/Feature | Item | Success/Fail
1 | Main Screen
1a |  | Game Loads properly to Main Screen
1b |  | UI elements change focus correctly
1c |  | Choosing <Start Game> functions correctly by placing the player in the game at the beginning of the first element
1d |  | Choosing <Exit Game> functions correctly closing out the game cleanly and places the player back in the platform interface
1e |  | Choosing <Load Game> functions correctly takes the player to the Save/Load Game system
1f |  | Choosing <Settings> functions correctly by taking you to the Player Setting System
2 | Performance
2a |  | Game loading time is within spec (loads within XX seconds)
2b |  | General game play shows no hitching or graphic errors
3 | Save Game
3a |  | Game save time is within spec (saves within XX seconds)
3b |  | Saved Game can be reloaded immediately
3c |  | Saved Game Data is correct on reloading
4 | Game Play

## Asset List
3D Models | [FBX]
Player
Body
Hats
Guard
Skeleton
Sword
Obsticles
Crate
Table
Environment
Floor
Wall
Background
Lamp
Ground
Animations | [FBX]
Player animation
Stand
Walk
Run
Crouch
Crouch walk
Jump
Guard animation
Stand
Walk
Sounds | [MP3]
Music
Title music
Tutorial music
Sound Effect
Foot steps SE
Jump SE
Land SE
Images | [PNG]
Texture
Wall texture
Background texture
UI
Font color
Title image
Fantasy castle path image
Game Over image
Fantasy castle dungeon image